## Provisional Implementation Outline for PROM/SE Capacity Building

| 2004/2005 Laying the Foundation: The Three Components of PROM/SE Capacity Building: Past activities Current activities ## Data, Leadership, Mathematics and Science |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ## Spring Mathematics Associate Orientation Introduction to PROM/SE | ## Summer Mathematics Associates Institute Introduction to the Work of PROM/SE (DATA) | ## Facilitator Workshops (Leadership) | ## Winter Mathematics Associates Institute (Mathematics and Data) | ## Curriculum Director Summit (Leadership and Data) | ## Facilitator Workshops (Leadership) |  |
| ## When | ## Spring, 2004 | ## August, 2004 ## 3 days | ## November, 2004 ## 1 day | ## December, 2004 ## 1.5 days | ## March 15, 2005 1 day | ## January – June, 2005 0.5 day |  |
| ## Who | ## Associates/ Administrators | ## Associates/Administrators | Associates/ invited | ## Associates/ Administrators | ## Curriculum Directors/Supervisors/ Principals | ## Associates/ optional |  |
| ## Goals | ## Learn about PROM/SE project and goals | ## Review initial data; overview of standards and coherent curriculum, begin to consider change process and components of leadership, and begin to define role of association. | ## Learn basic facilitation skills Begin to develop understanding of adult learners; Provide input on “task analysis” capacity building model for fall institutes | ## Review district and building data, analyze data and begin to make conjectures; consider relation of standards/benchmarks to understanding of fractions/algebra; learn how to interpret select statistical plots | ## Share local needs and issues. learn about PROM/SE and project goals, review initial data, develop strategies to support work with Associates, | ## Learn basic facilitation skills ## Begin to develop understanding of adult learners |  |
| ## Expectations |  | ## Plan and hold meetings with principal and colleagues to introduce PROM/SE project and goals Optional – use geometry curriculum focus with colleagues; use fraction meanings with colleagues | ## Assist session leaders at fall institutes | ## Begin initial data analysis with colleagues Optional – use task analysis with colleagues | ## Begin to implement plans for supporting associates; learn to work with PROM/SE data; identify specific local needs |  |  |
| ## Responsible | ## MSU Team and Partner Site | ## MSU Team and Partner Site | ## MSU Team | ## MSU Team and Partner Sites | ## MSU team to initiate planning, input from curriculum leaders and partners; attendees supported by MSU | ## Partners organize; MSU team support partners, costs and associates’ stipends from PROM/SE PD |  |

| 2004/2005 Laying the Foundation: The Three Components of PROM/SE Capacity Building: Past activities Current activities Data, Leadership, Mathematics and Science |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Activity | ## Spring Mathematics Associates Institute (Mathematics) | ## Curriculum Director Summit ## (Leadership) | # Science Associates Orientation on PROM/SE | Summer Science Academy (Data) |
| ## When | ## March/April, 2005 ## 1.5 days, 3 sites | ## May 5, 2005 ## 1 day | ## May, 2005 ## 0.5 day | ## June, 2005 ## 3 days, 3 sites |
| ## Who | ## Associates | ## Curriculum Directors/Supervisors/ Principals | ## Associates/Administrators | ## Associates/ administrators |
| ## Goals | Understand possible curriculum trajectories for a key mathematical concept; identify cognitive demand of tasks in own instructional materials Half day designed by partners | ## Review and plan for PROM/SE PD. Define role of associates, develop strategies to support work with Associates, | ## Learn about PROM/SE and project goals | ## Review district and building data, analyze data and begin to make conjectures; consider relation of standards/benchmarks to understanding of fractions/algebra; learn how to interpret select statistical plots |
| ## Expectations | ## Use materials from sessions as models for work in buildings/districts | ## Design plans for supporting associates Contribute to calendar setting | ## Meet with principal to consider how to introduce colleagues to PROM/SE | ## Plan and hold meetings with colleagues to begin to interpret science data |
| ## Responsible | ## MSU CB team to plan full day with input; Partners plan half day in accordance with goals; workshop costs and associates’ stipends from PROM/SE PD | ## MSU team to initiate planning, input from curriculum leaders and partners; attendees supported by MSU | ## MSU and Partner Sites | ## MSU and Partner Sites |

| ## 2005/6 Moving Ahead Based the Data |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Activity | Summer Mathematics Academy (Mathematics) | ## Mathematics Associates Institutes (Mathematics) | ## Fall Science Associates Institute (Science and Data) | ## Partner Site/District Inservice Sessions (Mathematics) |
| ## When | August, 2005 2 sites Michigan 5 days; Ohio 3 days | 2 days in fall term, 2005; 2 days in spring term, 2006 | 2 days in fall term 2005; 2 days in Spring term 2006 | ## September – May, 2005/6 4 days, targeted for Associates plus Regular meetings with associates and colleagues |
| ## Who | ## Teachers and associates | ## Associates | ## Associates | ## Associates/ Teachers |
| ## Goals | ## Strengthen content knowledge in area identified by PROM/SE data; courses designed for areas identified as student weakness. | ## Identify strategies for formative assessment; relate to curriculum ## Support associates as they begin working in districts |  | ## Designed by Partner site/districts to support PROM/SE and district goals |
| ## Expectations | ## Share deeper content knowledge with colleagues and use the mathematics and teaching strategies in their classrooms; | ## Conduct regular meetings centered on identified goals at school/district levels |  | ## Meetings at Partner site and/or district/school with support from Capacity Building consultants as needed. |
| ## Responsible | ## CB teams to organize and design; workshop costs and associates’ stipends from PROM/SE PD | ## CB Team to design, workshop costs and associates’ stipends from PROM/SE PD |  | ## Districts to organize/ Partners to approve plans, PROM/SE team provide support as needed, |

| ## 2005/6 Moving Ahead Based on the Data |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Activity | ## Targeted Mathematics Associates Institute | ## Science focused ## District sessions | ## Summer Science Academy |  |
| ## When | 4 days, schedule dependent on district and strand. | January – May, 2006 1 day | June, 2006 |  |
| ## Who | ## Associates/Curriculum Directors | ## Associates | ## Associates/ teachers |  |
| ## Goals | ## Targeted activities focused on leadership, content, or data | ## Support associates as they begin working with capacity building models; begin to work with online support |  |  |
| ## Expectations | ## Districts will increase focus on developing expertise in one of the three areas | ## Conduct regular meetings centered on identified goals at school/district levels |  |  |
| ## Responsible | ## CB Team to plan, workshop costs and associates’ stipends from PROM/SE PD | ## Partner Sites and/or Districts | ## MSU |  |

| ## Activity | ## Fall Science Associates Institute (Science and Data) | ## District Inservice Sessions (Mathematics/Leadership/ Data) |
| --- | --- | --- |
| ## When |  | ## September – May, 2006/7 Regular meetings with associates and colleagues |
| ## Who |  | ## Associates/ Teachers |
| ## Goals |  | ## Implementation of process to work on issues identified at district/building level |
| ## Expectations |  | ## Regular meetings at district with support from CB consultants/building as needed. |
| ## Responsible |  | ## Associates to organize/ Schools/districts and MSU to share |

| ## 2006/7 Building Capacity: Implementation |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Activity | ## Spring Mathematics Associate Institute | ## Science focused ## District sessions | ## Summer Science Academy??? |  |
| ## When | March/April, 2007 1.5 days |  | June |  |
| ## Who | ## Associates/Curriculum Directors |  | ## Associates/ teachers |  |
| ## Goals | ## Share strategies for formative assessment; share work in districts/schools; collect data on implementation |  |  |  |
| ## Expectations | ## Analyze data on implementation/ adjust as necessary |  |  |  |
| ## Responsible | ## CB Team to plan, workshop costs and associates’ stipends from PROM/SE PD |  |  |  |